## Slide 1: Scheduling Update
As of 06/11/2014

## Slide 2: Changes Since Last Report
Remedy ticket logged regarding New Enrollee Appointment Request (NEAR) issue
    Consist of three issues
      Appointment Request Date not being set in some cases
        Analysis in progress
      Possible corruption of the ^DPT(“AEAR” Cross-reference, which is used for the NEAR report
        Routine written to populate the missing entries, initial developer testing has begun
      Appointment Request Status is being set inappropriately
        Upon initial analysis, appears to be working properly. Further duplication efforts are being worked
    Requires further business process analysis and data logic flow
    Tier III elevated analysis to urgent status
    Resolution TBD
Initiative details and dates added
Legacy App Development/Deployment Status Updated
CVT program status updated
Comparison of VSE vs. MASS

## Slide 3: Leg App - Patches
TITLE | STATUS | DESCRIPTION | STATUS | EXPECTED COMPLETION DATE
SD*5.3*564 | Under Development | Addresses inconsistencies in list of patients selected and displayed in Primary Care Management Module (PCMM) GUI. | Tier II & III coordination ongoing | 6/30/2014
SD*5.3*579 | Released | Corrected recall reminder problems including undefined errors. |  | DONE
SD*5.3*582 | SQA Completed | Additional corrections of recall reminder problems including menu options and displays. Fixes an issue that allows user to select clinics which are inactive on the scheduled ate. Also fixes incorrect menu options and a display issue related to a second reminder. | Awaiting MOU approval from sites, then IOC begins | 7/31/2014
SD*5.3*585 | Field Test | Out of synch eligibility code corrections (affects displays) | Testing at IOC sites | 6/30/2014
SD*5.3*595 | Field Test | Correct appointment status in Appointment Management (affects display) Fixes a functionality issue where the incorrect status for an appointment has only been partially checked out. | 3 IOC sites installed patch to date | 7/31/2014
SD*5.3*604 | Under Development | Keep visit locked for SD (scheduling namespace) encounter entry. Prevents incomplete entries. | Development analysis & coding ongoing | 9/30/2014
SD*5.3*605 | SQA | Duplicate visits & truncated display of consult services (eliminates duplicate visits showing on the Patient Care Encounter (PCE) screen | SQA to be completed 6/11/2014 | 8/15/2014
SD*5.3*611 | Under Development | Corrects Electronic Wait List (EWL) issues involving creation of entries & displays. | Enter SQA 6/10/2014 | 9/20/2014
SD*5.3*615 | Under Development | FY2015 table maintenance for Clinic Stop Code file | Since this is tied to FY15, appropriate release date is start of FY15 | 9/30/2014
SD*5.3*618 | Under Development | Resolves appointment list sorting issues | Development analysis & coding ongoing | 9/30/2014

## Slide 4: Improved Interfaces for Schedulers and Patients
Clinical Video Teleconferencing (CVT)
  Automated, intra-facility web-based interface/system to perform scheduling for clinical video teleconferencing (CVT) and Telehealth instead of the existing manual processes
  Will deliver decreased wait times, increased scheduling efficiency, decreased frustration, and overall increased satisfaction with the nationwide CVT program
  April 2014: Implemented the Telehealth scheduling system in VISN 19 for user testing
  Received recommendation for waiver from 508 Office (POC: Pat Sheehan) June 9, 2014
  MS2 scheduled for June 12, 2014
  Coordinating with 508 office for near-term waiver. In parallel, fixes being addressed by 1QFY15, at which time full 508 compliance will be achieved.
Scheduling Manager App
  Changes view from “blue screen roll-and scroll” to a calendar picture view that pulls together relevant information in one screen needed to make an appointment.
  SCV app installed into the integration environment 6/16/2014
  V&V Functional Review - 6/30/2014
  Field testing starts – 8/11/2014
  IOC entry – 8/19/2014
  IOC exit – 10/14/2014
  National Release 11/12/2014
Patient Directed Scheduling App
  Allows patients to self-schedule selected appointment slots.
  Projected completion of initial programing April 1, 2015
  FOC: ~4th QFY15

## Slide 5: Near Term Solution – Enhancements to Core VISTA VistA Scheduling Enhancements (VSE)
Background
  VSE project was designed to provide critical, near-term enhancements to existing scheduling system in the absence of a new, COTS enterprise solution.
  Capabilities being released can be characterized in two ways- tools which will aid clinical managers in scheduling resources and enhancements to address recently identified vulnerabilities.
  Will deliver functionality that will provide users with a resource management dashboard, an aggregated clinical schedule, and a single queue of request lists and workflow improvements.
Timeline/Milestones
  Projected contract award: July 2014
  Development, Testing to be completed Q3 2015
  IOC and deployment to be completed Q2 2016

## Slide 6: Long Term Solution – Medical Appointment Scheduling Solution (MASS)
Proactive resource management-based scheduling that schedules staff, facilities, equipment
Provide transparency to balance supply with demand -
  Provide single, consolidate view of resource availability (e.g. one calendar for a clinician)
  Provide single, consolidate list of appointment requests (e.g. single view of the patient)
  Improved transparency through richer data for reporting
Provide consistent implementation and visibility of business rules to support scheduling policies and directives
Status
  High level business requirements developed
  Interested parties should review/respond to FedBizOpps Announcement Number VA118-14-I-0352
  Industry Day June 18, 2014, McLean, VA (sold out)
    Location MITRE-2 Building (N), The MITRE Corporation, 7515 Colshire Drive, McLean, VA
  Industry One-on-Ones June 30-July 2, Washington, DC (sold out)
    Location: VHA Conference Center, 2011 Crystal Drive, Crystal City, Virginia 22202
  MASS COTS/Development/Integration Award 4Q

## Slide 7: Comparison of VSE & MASS
VSE
Near term
Legacy
Contingency if MASS is not deployed on schedule
Critical/Focused Capability Enhancements
  Resource management dashboard
  Aggregated clinical schedule
  Single queue of request lists & workflow improvements
Schedule
  Contract Award July 2014
  Development, Testing completed Q3 2015
  IOC and deployment completed Q2 2016
MASS
Long term
Modern
Comprehensive
Capabilities
  Consistent, seamless, timely, high-quality scheduling interactions and healthcare appointments
  Resource–based scheduling
  Enhanced Enforcement/monitoring of policy
  Improved transparency of resources to be scheduled
  Leverages standardized data and business practices and full transparency across VHA to utilize resources efficiently, forecasting availability and balancing supply with demand
  Leverage s COTS to track episodes of care (vs. from one encounter to the next)
  Increased reporting capacity
  State-of-the-art Security
FY14/15 Schedule
  Industry events June 2014
  MASS COTS Development/Integration Award (tbd based on award date)
  Initial test environment and preliminary testing
  Planning for phased releases

## Slide 8
Chart: Long-term Project Totals
| FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | Totals
Medical Appointment Scheduling System (MASS) | 19.867 | 60.68 | 86.88 | 72 | 76 | 80.2 | 59.2 | 454.827
Project |  | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | Totals
Medical Appointment Scheduling System (MASS) | Pay | 0.267 | 10.680 | 10.680 | 4.000 | 4.000 | 4.000 | 4.000 | 37.627
 | Non-Pay DME | 19.600 | 48.000 | 63.800 | 50.000 | 61.900 | 63.800 | 38.700 | 345.800
 | Non-Pay SUS | 0.000 | 2.000 | 12.400 | 18.000 | 10.100 | 12.400 | 16.500 | 71.400
 | Total | 19.867 | 60.680 | 86.880 | 72.000 | 76.000 | 80.200 | 59.200 | 454.827

## Slide 9
Chart: Short-term Project Totals
| FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | Totals
VistA Scheduling Enhancement (VSE) | 3.767 | 1.767 | 0.515 | 0.53 | 0.546 | 0.563 | 0.58 | 8.268
Clinical Video Teleconferencing (CVT) | 2.445 | 4.936 | 1.342 | 0 | 0 | 0 | 0 | 8.723
Clinical Video Teleconferencing (CVT) Phase 2 | 0 | 3.297 | 3.455 | 1.455 | 1.505 | 1.58 | 1.659 | 12.951
Schedule Calendar View (SCV) | 2.533 | 3.233 | 0 | 0 | 0 | 0 | 0 | 5.766
Project |  | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | Totals
VistA Scheduling Enhancement (VSE) | Pay | 0.267 | 0.267 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.534
 | Non-Pay DME | 3.500 | 1.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 4.500
 | Non-Pay SUS | 0.000 | 0.500 | 0.515 | 0.530 | 0.546 | 0.563 | 0.580 | 3.234
 | Total | 3.767 | 1.767 | 0.515 | 0.530 | 0.546 | 0.563 | 0.580 | 8.268
Clinical Video Teleconferencing (CVT) | Pay | 0.135 | 0.135 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.270
 | Non-Pay DME | 2.310 | 2.310 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 4.620
 | Non-Pay SUS | 0.000 | 2.491 | 1.342 | 0.000 | 0.000 | 0.000 | 0.000 | 3.833
 | Total | 2.445 | 4.936 | 1.342 | 0.000 | 0.000 | 0.000 | 0.000 | 8.723
Clinical Video Teleconferencing (CVT) Phase 2 | Pay | 0.000 | 0.133 | 0.133 | 0.022 | 0.000 | 0.000 | 0.000 | 0.288
 | Non-Pay DME | 0.000 | 1.864 | 1.957 | 0.000 | 0.000 | 0.000 | 0.000 | 3.821
 | Non-Pay SUS | 0.000 | 1.300 | 1.365 | 1.433 | 1.505 | 1.580 | 1.659 | 8.842
 | Total | 0.000 | 3.297 | 3.455 | 1.455 | 1.505 | 1.580 | 1.659 | 12.951
Schedule Calendar View (SCV) | Pay | 0.133 | 0.133 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.266
 | Non-Pay DME | 2.300 | 3.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 5.300
 | Non-Pay SUS | 0.100 | 0.100 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 0.200
 | Total | 2.533 | 3.233 | 0.000 | 0.000 | 0.000 | 0.000 | 0.000 | 5.766
Short-term Project Totals |  | 8.745 | 13.233 | 5.312 | 1.985 | 2.051 | 2.143 | 2.239 | 35.708

## Slide 10: Back Up Material

## Slide 11: History
2009: VA cancels a 10 year+ medical scheduling replacement project that failed to deliver
2010: VA conducts intense after-action analysis; identifies key risks
  Among corrective actions: PMAS
2011: VA releases RFI: asks industry about its capability to create an open source modular scheduling product and connect it to VistA
  35 responses received from broad cross section of industry
  Industry says it can meet VA’s scheduling requirements with range of open architectures; multiple attractive options
2012/2013: Medical Scheduling Contest via America Competes Act
  Contest launched: Requires open source solutions.
  Did not provide a sufficiently mature solution and were not in alignment with VA enterprise architecture